## Plan
| ISO : F3.5 | [58 empty] | 43844.6605
| DATE | 2017-07-01 |  |  | 2017-07-02 |  |  | 2017-07-03 |  |  | 2017-07-04 |  |  | 2017-07-05 |  |  | 2017-07-06 |  |  | 2017-07-07 |  |  | 2017-07-08 |  |  | 2017-07-09 |  |  | 2017-07-10 |  |  | 2017-07-11 |  |  | 2017-07-12 |  |  | 2017-07-13 |  |  | 2017-07-14 |  |  | 2017-07-15 |  |  | 2017-07-16 |  |  | 2017-07-17 |  |  | 2017-07-18 |  |  | 2017-07-19 |  |  |  | 2020-01-14 |  |  | 2020-01-15 |  |  | 2020-01-16 |  | 2017-07-23
| SHIFT | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D
CP19 | PROJECT SECTION (MIR) | C762A-15MT HT60X60X5 41076933 | C762A-15MT HT60X60X5 41076933 | C762A-15MT HT60X60X5 41076933 | C762A-1.5MT HT75X75X6 41077115 | C792A-13MT MS70X70X5 41077128 | C792A-13MT MS70X70X5 41077128 | C792A-13MT MS70X70X5 41077128 | B7591D-0.5MT L55X55X4 41076971 | C639CT-4MT L60X60X5 41076842 | C639CT-4MT L60X60X5 41076842 | C639T-5.2MT L50X50X5 41076841 | C762A-26.MT L50X50X5 41076939 | C762A-26.MT L50X50X5 41076939 | C762A-26.MT L50X50X5 41076939 | C762A-26.MT L50X50X5 41076939 | C762A-26.MT L50X50X5 41076939 | C762A-26.MT L50X50X5 41076939 | C762A-12MT L50X50X5 41077119 | C762A-12MT L50X50X5 41077119 | C762A-12MT L50X50X5 41077119 | C762A-12MT L50X50X5 41077119 | C762A-12MT L50X50X5 41077119 | C762A-12MT L50X50X5 41077119 | C639CT-4MT L60X60X5 41076842 | C639CT-4MT L60X60X5 41076842 | C639CT-1MT L MIX 41077045/230/231 | C762A-27MT L50X50X5 41077149 | C762A-27MT L50X50X5 41077149 | C762A-24MT L50X50X5 41076941 | C762A-24MT L50X50X5 41076941 | C762A-24MT L50X50X5 41076941 | C762A-24MT L50X50X5 41076941 | C639CT-1MT L MIX 41077045/230/231 | N602-7MT L55X55X5 41077256 | N602-7MT L55X55X5 41077256 | N602-7MT L55X55X5 41077256 | N602-1MT L50X50X5 41077316 | C762A-20MT L70X70X5 41077488 | C762A-20MT L70X70X5 41077488 | C762A-20MT L70X70X5 41077488 | C762A-20MT L70X70X5 41077488 | C762A-20MT L70X70X5 41077488 | C762A-22MT L65X65X5 41077232 | C762A-22MT L65X65X5 41077232 | C762A-22MT L65X65X5 41077232 | C762A-22MT L65X65X5 41077232 | C762A-1.5MT L60X60X5 41077548 | C762A-1.5MT L60X60X5 41077548 | C762A-21MT L70X70X5 41077547 | C762A-21MT L70X70X5 41077547 | C762A-21MT L70X70X5 41077547 | C762A-21MT L70X70X5 41077547 | C762A-21MT L70X70X5 41077547 | C762A-21MT L70X70X5 41077547 | C762A-21MT L70X70X5 41077547 | C762A-6.5MT L70X70X5 41077538 | C762A-8.5MT L50X50X5 41077624 | M45X5(000080134527)(0S806) | M50X4(000080133309)(TC922) | M55X4(000080134532)(0S806) | M55X4(000080134532)(0S806) | M65X4(000080134304)(TB901)
| TOTAL WEIGHT | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 301 | 317 | 317 | 317 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 317 | 317 | 314 | 2 | 2 | 2 | 2 | 2 | 2 | 314 | 52/53/54 | 52/53/54 | 52/53/54 | 53/54 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 1044.46 | 3585.928 | 4882.496 | 3314.468 | 120.02
| NO. OF SET UPS | [8 empty] | 35 | 35 | [13 empty] | 35 | 35 | [12 empty] | 10700 MM LENGTH | 10700 MM LENGTH | 10700 MM LENGTH | 10700 MM LENGTH | 10700 MM LENGTH | 9600 | 9600 | 9600 | 9600 |  |  |  |  | BD | BD | RE | RE | RE | 1700 |  | 16 | 28 | 44 | 36 | 5 | 0 | 0 | 0 | 0
| NO OFOPERATION |  |  |  | 3000 | 3600 | 3600 | 3600 |  |  |  |  | N | N | N | N | N | N | [8 empty] | Not run as per paln | 102 plan | 102 plan | 14 | 14 | 14 | 14 |  | 118 | 118 | 118 |  | DIRECT ISSUE | DIRECT ISSUE | DIRECT ISSUE | DIRECT ISSUE | DIRECT ISSUE | 1067 MIN | 1067 MIN | 1067 MIN | 1067 MIN | 885 MIN | 885 MIN | 886 MIN | 886 MIN | 886 MIN | 886 MIN | 886 MIN | 886 MIN | 886 MIN |  | 571 MIN | 1798 | 0 | 4128 | 2960 | 47
| SECONDARY LOAD | [57 empty] | N+ | N+ | B+W+N+ | N+ | B+N+
| CAL. RUN TIME | n+s | n+s | n+s | S | N | N | N | S | N+S | N+S | N+B | N | N | N | N | N | N | N+S | N+S | N+S | N+S | N+S | N+S | N+S | N+S | N | N+B | N+B | N+S | N+S | N+S | N+S | N | N+B | N+B | N+B | N | N | N | N | N | N | N | N | N | N | HG | HG | N+S | N+S | N+S | N+S | N+S | N+S | N+S | N | N+S | 0 | 508.1581 | 518.0252 | 518.0252 | 0
CP20 | PROJECT SECTION (MIR) | N712A-2MT L40X40X4 41077063 | C762A-24MT L50X50X5 41076935 | C762A-24MT L50X50X5 41076935 | C762A-24MT L50X50X5 41076935 | C762A-24MT L50X50X5 41076935 | C762A-24MT L50X50X5 41076935 | C762A-24MT L50X50X5 41076935 | C762A-24MT L50X50X5 41076935 | C639LM-5MT L50X50X5 41077044 | C639LM-5MT L50X50X5 41077044 | C639LM-5MT L50X50X5 41077044 | C762A-25MT L50X50X5 41076943 | C762A-25MT L50X50X5 41076943 | C762A-25MT L50X50X5 41076943 | C762A-25MT L50X50X5 41076943 | C762A-25MT L50X50X5 41076943 | C762A-25MT L50X50X5 41076943 | C762A-25MT L50X50X5 41076943 | C762A-25MT L50X50X5 41076943 | C762A-16MT L50X50X5 41077118 | C762A-16MT L50X50X5 41077118 | C762A-16MT L50X50X5 41077118 | C762A-16MT L50X50X5 41077118 | A623S-0.6MT L45X45X4 41077164 | C762A-24MT L50X50X5 41076941 | C762A-24MT L50X50X5 41076941 | C762A-24MT L50X50X5 41076941 | C762A-24MT L50X50X5 41076941 | C762A-27MT L50X50X5 41077149 | C762A-27MT L50X50X5 41077149 | C762A-27MT L50X50X5 41077149 | C762A-27MT L50X50X5 41077149 | C762A-27MT L50X50X5 41077149 | C762A-27MT L50X50X5 41077149 | C762A-27MT L50X50X5 41077149 | C762A-12MT L50X50X5 41077223 | C762A-12MT L50X50X5 41077223 | C762A-12MT L50X50X5 41077223 | C762A-13MT L50X50X5 41077224 | C762A-13MT L50X50X5 41077224 | C762A-6MT L50X50X5 41077225 | C762A-6MT L50X50X5 41077225 | C762A-15MT L50X50X5 41077549 | C762A-15MT L50X50X5 41077549 | C762A-15MT L50X50X5 41077549 | C639-8MT L45X45X5 41077510 | C639-8MT L45X45X5 41077510 | C639-8MT L45X45X5 41077510 | C639-8MT L45X45X5 41077510 | C639/C762A-1MT L65X5(41077455) L50X6(41077512) | C639/C762A-1MT L65X5(41077455) L50X6(41077512) | C639/C762A-1MT L65X5(41077455) L50X6(41077512) | A621DD-3.5MT L45X45X4 41077584 | A621DD-3.5MT L45X45X4 41077584 | A621DD-3.5MT L45X45X4 41077584 | C762A-10MT L50X50X5 41077612 | C762A-10MT L50X50X5 41077612 | H45X4(000080135069)(TC922)
| TOTAL WEIGHT | 300 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 314 | 314 | 314 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 37 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 310 | 310 | 310 | 310 | 4/331 | 4/331 | 4/331 | 84 | 84 | 84 | 2,3 | 2,3 | 9664.452
| NO. OF SET UPS | 174 | [23 empty] | 160 plan | 160 plan | 160 plan | 160 plan | 6 shift | 6 shift | 6 shift | 6 shift | 6 shift | 6 shift | 6 shift | [17 empty] | 205 | 205 | 205 |  |  | 142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| NO OFOPERATION | [57 empty] | 0
| SECONDARY LOAD |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | [11 empty] | 1293 MIN | 1293 MIN | 1293 MIN | 1293 MIN |  | 14 | 14 | 14 | 14 |  |  |  | BD/2 | no operator | DB/2 |  | 3 | 3 | 3 | 3 | 3 |  |  | 1778 MIN | 1778 MIN | 1778 MIN | 119 | 119 | 119 | 119 | [6 empty] | 761 MIN | 761 MIN | N+N+B+
| CAL. RUN TIME | N | N | N | N | N | N | N | N | N+B+ | N+B+ | N+B+ | NB+ | NB+ | NB+ | NB+ | NB+ | NB+ | NB+ | NB+ | S | S | S | S | N+S | N+S | N+S | N+S | N+S | N+B | N+B | N+B | N+B | N+B |  | N+B | N+B | N+B | N+B | N+B | N+B | N | N | N | N | N | N+B | N+B | N+B | N+B | N+HG | N+HG | N+HG | N+B | N+B | N+B | N+B | N+B | 1896.44
CP21 | PROJECT SECTION (MIR) | C762A-8MT H75X75X5 41077114 | C762A-1.5MT L100X100X6 41077898 | C762A-8MT H75X75X5 41077114 | C762A-8MT H75X75X5 41077114 | C762A-21MT MS70X70X5 41077093 | C762A-21MT MS70X70X5 41077093 | C762A-8MT H75X75X5 41077114 | C639/B759-2MT L MIX 41076845/965//972/964/834 | C639CT-5MT LMIX 41076828/29/082 | C762A-1.5MT HT75X75X6 41077115 | C639/B759-2MT L MIX 41076845/965//972/964/834 | C639CT-5MT LMIX 41076828/29/082 | C639CT-3MT L MIX 41076831/832/833/839/830/043 | C762A-24MT L70X70X5 41077126 | C762A-24MT L70X70X5 41077126 | C762A-24MT L70X70X5 41077126 | C762A-24MT L70X70X5 41077126 | C762A-1MT L80X80X6 41077156 | C639CT-8MT L MIX 41076828/29/31/32/33/39/043 | C639CT-8MT L MIX 41076828/29/31/32/33/39/043 | C762A-6MT L70X70X5 41077126 | C762A-6MT L70X70X5 41077126 | C762A-1.5MT L75X75X6 41077148 | C762A-11MT L80X80X6 41077185 | C762A-11MT L80X80X6 41077185 | C762A-1.5MT L100X100X6 41077167 | C762A-10MT L90X90X6 41077189 | N602Q/S-4MT LMIX 41077262/197/833 | C762A-1.5MT L75X75X6 41077148 | C762A-12MT L90X90X6 41077188 | C762A-12MT L90X90X6 41077188 | C762A-12MT L90X90X6 41077188 | ITEM NOC762A-23,24,25,32,33 L70X70X5 41077414 LENGTH 10700/800PCS | ITEM NOC762A-23,24,25,32,33 L70X70X5 41077414 LENGTH 10700/800PCS | ITEM NOC762A-23,24,25,32,33 L70X70X5 41077414 LENGTH 10700/800PCS | ITEM NOC762A-23,24,25,32,33 L70X70X5 41077414 LENGTH 10700/800PCS | ITEM NOC762A-23,24,25,32,33 L70X70X5 41077414 LENGTH 10700/800PCS | ITEM NOC762A-23,24,25,32,33 L70X70X5 41077414 LENGTH 10700/800PCS | ITEM NOC762A-23,24,25,32,33 L70X70X5 41077414 LENGTH 10700/800PCS | C762A-21MT L70X70X5 41077489 | C762A-21MT L70X70X5 41077489 | C762A-21MT L70X70X5 41077489 | C762A-25MT L70X70X5 41077529 | C762A-25MT L70X70X5 41077529 | C762A-25MT L70X70X5 41077529 | C762A-14MT L75X75X5 41077244 | C762A-14MT L75X75X5 41077244 | C762A-21MT L70X70X5 41077533 | C762A-14MT L75X75X5 41077244 | C762A-15MT L70X70X5 41077563 | C762A-15MT L70X70X5 41077563 | C762A-21MT L70X70X5 41077533 | C762A-21MT L70X70X5 41077533 | C762A-1MT L70X70X5 41077579 | C762A-21MT L70X70X5 41077533 | C762A-1MT L70X70X5 41077579 | C762A-21MT L70X70X5 41077533 |  |  |  | H100X7(000080135451)(TC928) | H100X7(000080135451)(TC928) | H75X5(000080135494)(TC922)M60X4(000080135251)(TC922)M60X4(000080135252)(TC928)
| TOTAL WEIGHT | 1 | 6 | 1 | 1 | 1 | 1 | 1 | 301/317 | 317 | 1 | 301/317 | 317 | 317 | 2 | 2 | 2 | 2 | 1 | 317 | 317 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 54/52 | 2 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 3 | 3 | 4 | 4 | 2,3 | 4 | 2,3 | 4 |  |  |  | 12329.1361 | 12329.1361 | 3375.216
| NO. OF SET UPS | [9 empty] | transfer from 160 | [8 empty] | 41 | 41 |  |  | NOT RUN AS P | [5 empty] | rp |  |  |  | NOT RUN(T3 ROUT SHHET RUN) | DIRECT UNLOAD | DIRECT UNLOAD | DIRECT UNLOAD | DIRECT UNLOAD | DIRECT UNLOAD | DIRECT UNLOAD | DIRECT UNLOAD | DIRECT UNLOAD | DIRECT UNLOAD | 4 | 4 | 4 | [12 empty] | 0 | 0 | 0 | 27 | 27 | 11 | 0 | 0 | 0
| NO OFOPERATION | 11000 |  | 11000 | 11000 | 10500 | 10500 | 11000 |  |  | 3000 |  |  |  | BD | BD | BD | BD | 5600 | BD |  |  |  | 3500 | 10000 | 10000 | 7200 | 2600 |  | 3500 | 14000 | 14000 | 14000 | 1715 MIN | 1715 MIN | 1715 MIN | 1715 MIN | 1715 MIN | 1715 MIN | 1715 MIN |  |  |  | 1270 MIN | 1270 MIN | 1270 MIN | 537 MIN | 537 MIN | 885 MIN | 537 MIN |  |  | 885 MIN | 885 MIN | 3200 | 885 MIN | 3200 | 885 MIN |  |  |  | 10928 | 10928 | 144
| SECONDARY LOAD | 3600 | 3600 | 7000 | 7000 | 12400 | 12400 | 20000 | 20000 | 20000 | 20000 | 22000 | 22000 | 22000 | 9000 | 2600 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | NOT RUN AS P | NOT RUN AS P | [5 empty] | 20000 | 20000 | 20000 | 20000 | 21500 | 21500 | 21500 | 740 | 740 | 881 | 881 |  |  |  |  | 1270 MIN | 1270 MIN | 1270 MIN | 1270 MIN | 1270 MIN | 1270 MIN | 1273 MIN | 1273 MIN | 1273 MIN | 1273 MIN | 801 MIN | 801 MIN | 801 MIN | 801 MIN |  |  |  | N+ | N+ | N+
| CAL. RUN TIME | N+B+HG | CLAETS | N+B+HG | N+B+HG | N+S | N+S | N+B+HG | N+B | N+W | S | N+B | N+W | N | N+ | N+ | N+ | N+ | HG | N | N | N | N | S | S | S | HG | B | N+B | S | B+S | B+S | B+S | N | N | N | N | N | N | N | N | N | N | N+S | N+S | N+S | N | N | N | N | N+B | N+B | N | N | HG | N | HG | N |  |  |  | 0 | 0 | 183.297
CP01 | PROJECT SECTION (MIR) | C762A-14MT MS75X75X5 41076945 | C762A-14MT MS75X75X5 41076945 | C762A-8MT H80X80X6 41077141 | C762A-8MT H80X80X6 41077141 | C762A-40MT H130X130X12 41077107 | C762A-40MT H130X130X12 41077107 | C762A-58MT L130X130X10 41077055 | C762A-58MT L130X130X10 41077055 | C762A-58MT L130X130X10 41077055 | C762A-58MT L130X130X10 41077055 | C762A-6MT L110X110X8 41077089 | C762A-6MT L110X110X8 41077089 | C762A-6MT L110X110X8 41077089 | C762A-19MT L130X130X10 41077057 | C762A-10MT L90X90X6 41077116 | C762A-40MT L130X130X12 41077166 | C762A-40MT L130X130X12 41077166 | C762A-40MT L130X130X12 41077177 | C762A-40MT L130X130X12 41077177 | C762A-40MT L130X130X12 41077177 | C762A-40MT L130X130X12 41077177 | C762A-12MT L120X120X10 41077165/176 | C762A-12MT L120X120X10 41077165/176 | C762A-12MT L120X120X10 41077165/176 | C762A-12MT L120X120X10 41077165/176 | C762A-12MT L120X120X10 41077165/176 | C762A-12MT L120X120X10 41077165/176 | C762A-12MT L120X120X10 41077165/176 | C762A-58MT L130X130X10 41077170 | C762A-58MT L130X130X10 41077170 | C762A-58MT L130X130X10 41077170 | C762A-58MT L130X130X10 41077170 | C762A-58MT L130X130X10 41077220 | C762A-58MT L130X130X10 41077220 | C762A-58MT L130X130X10 41077220 | C762A-28MT L120X120X10 41077218 | C762A-28MT L120X120X10 41077218 | C762A-28MT L120X120X10 41077219 | C762A-28MT L120X120X10 41077219 | C762A-19MT L130X130X10 41077283 | C762A-22MT L70X70X5 41077490 | C762A-22MT L70X70X5 41077490 | C762A-22MT L70X70X5 41077490 | C762A-25MT L70X70X5 41077530 | C762A-25MT L70X70X5 41077530 | C762A-25MT L70X70X5 41077530 | C762A-25MT L70X70X5 41077530 | C762A-25MT L70X70X5 41077530 | C762A-25MT L70X70X5 41077530 | C762A-24MT L70X70X5 41077536 | C762A-24MT L70X70X5 41077536 | C762A-24MT L70X70X5 41077536 | C762A-24MT L70X70X5 41077536 | C762A-15MT L80X80X6 41077572 | C762A-15MT L80X80X6 41077572 | C762A-15MT L80X80X6 41077573 | C762A-15MT L80X80X6 41077573 |  |  |  | H110X8(000080135173)(TC922) | H110X8(000080135173)(TC922) | H110X8(000080135173)(TC922)
| TOTAL WEIGHT | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 8 | 8 | 8 | 8 | 8 | 8 | 8,9 | 8,9 | 8,9 | 8,9 | 8,9 | 8,9 | 8,9 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 3 |  |  |  | 24582.518 | 24582.518 | 24582.518
| NO. OF SET UPS | [10 empty] | 2 | 2 | 2 |  |  | NOT RUN AS PER PLAN RUN T3 77116 | [12 empty] | 3 | 3 | BD | 3 | 1553 MIN | 3 | 3 | 1 | 1 | 1 | 1 |  | 3 | 3 | 3 | [10 empty] | DIRECT ISSUE | DIRECT ISSUE | DIRECT ISSUE | DIRECT ISSUE | 0 | 0 | 0 | 22 | 22 | 22 | 0 | 0 | 0
| NO OFOPERATION | 10000 | 10000 | 10000 | 10000 | 10000 | 7500 | 7500 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 6400 | 2600 |  | 3600 | 3 | 3 | 3 | 16000 | 16000 | 16000 | [5 empty] | 1772 MIN | 1772 MIN | 1772 MIN | 1772 MIN | 1772 MIN | 34 | 27400 | 27400 | 27400 | 27400 | 27400 | 395 MIN |  |  |  | 2 | 1 | 2 | 2 | 2 | 840 MIN | 840 MIN | 840 MIN | 55 ITEM | 55 ITEM |  | 55 ITEM |  |  |  |  | 0 | 0 | 0
| SECONDARY LOAD | 3600 | 3600 | 7000 | 7000 | 12400 | 12400 | 20000 | 20000 | 20000 | 20000 | 22000 | 22000 | 22000 | 9000 | 2600 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | NOT RUN AS P | NOT RUN AS P | [5 empty] | 20000 | 20000 | 20000 | 20000 | 21500 | 21500 | 21500 | 740 | 740 | 881 | 881 |  |  |  |  | 1270 MIN | 1270 MIN | 1270 MIN | 1270 MIN | 1270 MIN | 1270 MIN | 1273 MIN | 1273 MIN | 1273 MIN | 1273 MIN | 801 MIN | 801 MIN | 801 MIN | 801 MIN |  |  |  | B+N+N+B+ | B+N+N+B+ | B+N+N+B+
| CAL. RUN TIME | S | S | S | S | S | S | S | S | S | S | HG | HG | HG | S | B | STUB | STUB | STUB | STUB | STUB | STUB | STUB CLEATS | STUB CLEATS | STUB CLEATS | STUB CLEATS | STUB CLEATS | STUB CLEATS | STUB CLEATS | S | S | S | S | S | S | S | B | B | B | B | S | N+S | N+S | N+S | S+N | S+N | S+N | S+N | S+N | S+N | N+S | N+S | N+S | N+S | B | B | B | B |  |  |  | 330.5366 | 330.5366 | 330.5366
CP02 | PROJECT SECTION (MIR) | C762A-12MT L90X90X6 41077117 | C762A-12MT L90X90X6 41077117 | C762A-12MT L90X90X6 41077117 | C762A-19MT L130X130X10 41077056 | C762A-19MT L130X130X10 41077056 | C762A-14MT L120X120X10 41076901 | C762A-14MT L120X120X10 41076743 | C762A-58MT L130X130X10 41077054 | C762A-58MT L130X130X10 41077054 | C762A-58MT L130X130X10 41077054 | C762A-58MT L130X130X10 41077054 | C762A-58MT L130X130X10 41077054 | C762A-58MT L130X130X10 41077054 | C762A-58MT L130X130X10 41077054 | C762A-15MT L80X80X6 41077140 | C762A-10MT L90X90X6 41077116 | E701OE-1MT L65X6(77287) L75X8(77288) | C639-11.5MT L110X110X8 41077071 | C762A-16MT L80X80X6 41077184 | C762A-16MT L80X80X6 41077184 | C762A-16MT L80X80X6 41077184 | C762A-23MT L80X80X6 41077157 | C762A-23MT L80X80X6 41077157 | C762A-23MT L80X80X6 41077157 | N602Q/S-4MT LMIX 41077245/246/262 | C762A-7MT L75X75X5 41077195 | C762A-1MT L75X75X5 41077196 | C762A-15MT L80X80X6 41077187 | C762A-15MT L80X80X6 41077187 | ITEM NOC762A-26,27,34,35 L70X70X5 41077414 LENGTH 9850/800PCS | ITEM NOC762A-26,27,34,35 L70X70X5 41077414 LENGTH 9850/800PCS | ITEM NOC762A-26,27,34,35 L70X70X5 41077414 LENGTH 9850/800PCS | ITEM NOC762A-26,27,34,35 L70X70X5 41077414 LENGTH 9850/800PCS | ITEM NOC762A-26,27,34,35 L70X70X5 41077414 LENGTH 9850/800PCS | N602-3MT L70X5,90X6 41077321,22,23,24,20 | C762A-34MT L110X110X8 41077390 | C762A-34MT L110X110X8 41077390 | C762A-34MT L110X110X8 41077390 | C762A-34MT L110X110X8 41077390 | N602/C762A-34MT L110X110X8 41077390/246 | N602/C762A-9 MT L110X110X8 41077399/370 | C762A-20MT L90X90X6 41077235 | C762A-20MT L90X90X6 41077235 | C762A-2MT L90X90X6 41077236 | C762A-1.2MT L75X75X6 41077234 | C762A-1.2MT L100X100X6 41077217 | C762A-15MT L80X80X6 41077335 | C762A-15MT L80X80X6 41077335 | C762A-15MT L80X80X6 41077335/234 | C762A-21MT L70X70X5 41077534 | C762A-21MT L70X70X5 41077534 | C762A-21MT L70X70X5 41077534/234 | N602-6MT L65X65X5 41077565/566 | N602-6MT L65X65X5 41077565/566 | C762A-5MT L70X70X5 41077567/568/566 | N602-6MT L65X65X5 41077565/566 | C762A-5MT L70X70X5 41077567/568 |  |  |  | H100X7(000080135453)(TC922)M80X5(000080135308)(TC922) | H100X7(000080135453)(TC922) | M75X5(000080135304)(TC922)M80X5(000080135308)(TC922)
| TOTAL WEIGHT | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 6 | 2 | 2 | 2 | 2 | 2 | 2 | 54/52 | 3 | 3 | 3 | 3 | LOT NO 2 | LOT NO 2 | LOT NO 2 | LOT NO 2 | LOT NO 2 | 52/53/54 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 52/54 | 52/54 | 2,3 | 52/54 | 2,3 |  |  |  | 22186.376 | 19317.096 | 5283.544
| NO. OF SET UPS | [6 empty] | PL IN SHOP | [8 empty] | RUN ON CP06 | RAILWAYS | 412 MIN | 11600 | 11600 | 11600 | RUNNING ON CP04 | RUNNING ON CP04 | [6 empty] | NOT RUN AS PELAN | DIRECT UNLOAD | DIRECT UNLOAD | DIRECT UNLOAD | DIRECT UNLOAD | T4 PLAN SHIFTED |  |  |  | NO OPERATOR |  | MIR NO 370 NOT RUN |  |  | 5 | NOT RUN |  |  |  | mir no 234 not run | [8 empty] | 0 | 0 | 0 | 26 | 20 | 10 | 0 | 0 | 0
| NO OFOPERATION | 10000 | 10000 | 10000 | 10000 | 10000 | 7500 | 7500 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 6400 | 2600 |  | 3600 | 3 | 3 | 3 | 16000 | 16000 | 16000 | [5 empty] | 1772 MIN | 1772 MIN | 1772 MIN | 1772 MIN | 1772 MIN | 34 | 27400 | 27400 | 27400 | 27400 | 27400 | 395 MIN |  |  |  | 2 | 1 | 2 | 2 | 2 | 840 MIN | 840 MIN | 840 MIN | 55 ITEM | 55 ITEM |  | 55 ITEM | no operator |  |  |  | 0 | 0 | 0
| SECONDARY LOAD | 3600 | 3600 | 7000 | 7000 | 12400 | 12400 | 20000 | 20000 | 20000 | 20000 | 22000 | 22000 | 22000 | 9000 | 2600 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | NOT RUN AS P | NOT RUN AS P | [5 empty] | 20000 | 20000 | 20000 | 20000 | 21500 | 21500 | 21500 | 740 | 740 | 881 | 881 |  |  |  |  | 1270 MIN | 1270 MIN | 1270 MIN | 1270 MIN | 1270 MIN | 1270 MIN | 1273 MIN | 1273 MIN | 1273 MIN | 1273 MIN | 801 MIN | 801 MIN | 801 MIN | 801 MIN |  |  |  | B+N+N+B+ | B+N+N+B+ | N+
| CAL. RUN TIME | S | S | S | S | S | B | B | S | S | S | S | S | S | S | B | B | B | S | B | B | B | S | S | S | N+B | B+S | HG | B+S | B+S | N | N | N | N | N | N+S | S | S | S | S | S | S | B | B | S | S | HG | B | B | B | N | N | N | N+B | N+B | B | N+B | B |  |  |  | 473.4433 | 348.112 | 233.7272
CP03 | PROJECT SECTION (MIR) | C762A-34MT H110X110X8 41077088 | C762A-34MT H110X110X8 41077088 | C762A-34MT H110X110X8 41077088 | C762A-6MT L120X120X10 41077105 | C762A-6MT L120X120X10 41077105 | C762A-21MT MS70X70X5 41077093 | C762A-21MT MS70X70X5 41077093 | C762A-1.5MT HT75X75X6 41077115 | C762A-23MT L70X70X5 41077130 | C762A-23MT L70X70X5 41077130 | C762A-23MT L70X70X5 41077130 | C762A-23MT L70X70X5 41077130 | C762A-23MT L70X70X5 41077130 | C762A-23MT L70X70X5 41077130 | C6392T-2MT L MIX 41077046/083/084 | C639-1MT L65X65X6 41077047 | /C762/C6392T-2MT L MIX 41077046/083/084/154 | C639-1MT L65X65X6 41077047 | C762A-1MT L80X80X6 41077156 | N712A-1.5+N602-3 MT L MIX 41077058/059/77070 | C762A-6MT L110X110X8 41077090 | C762A-6MT L110X110X8 41077090 | C762A-6MT L110X110X8 41077090 | C762A-16MT L110X110X8 41077145 | C762A-16MT L110X110X8 41077145 | C762A-1.2MT L75X75X6 41077197 | C762A-16MT L110X110X8 41077145 | C762A-16MT L110X110X8 41077145 | N712A-1.5+N602-3 MT L MIX 41077058/059/77070 | C762A-4MT L60X60X5 41077284/285 | C762A-1.2MT L75X6 41077148 | N602-3MT L70X5,90X6 41077321,22,23,24,20 | N602-3MT L70X5,90X6 41077321,22,23,24,20 | C762A-34MT L110X110X8 41077391 | C762A-34MT L110X110X8 41077391 | C762A-34MT L110X110X8 41077391 | C762A-34MT L110X110X8 41077391 | N602-3MT L70X5,90X6 41077321,22,23,24,20 | C762A-6.2MT L110X110X8 41077334 | C762A-6.2MT L110X110X8 41077334 | C762A-6.2MT L110X110X8 41077334 | C762A-20MT L70X70X5 41077532 | C762A-20MT L70X70X5 41077532 | C762A-6.2MT L110X110X8 41077392 | C762A-6.2MT L110X110X8 41077392 | C762A-6.2MT L110X110X8 41077392 | C762A-20MT L70X70X5 41077532 | C762A-20MT L70X70X5 41077532 | C762A-20MT L70X70X5 41077532 | N602-2.8MT L MIX 41077322/323/370 | N602/C639-3MT LMIX 41077539/541/543/446/462 | C762A-24MT L70X70X5 41077545 | N602/C639-3MT LMIX 41077539/541/543/446/462/323 | C762A-24MT L70X70X5 41077545 | N602/C639-3MT LMIX 41077539/541/543/446/462/323 | A621DD-4MT L MIX 41077440/479 | A621DD-4MT L MIX 41077440/479 |  |  |  | H110X8(000080135013)(TC922) | H100X8(000080134762)(0S806) | H100X8(000080134762)(0S806)
| TOTAL WEIGHT | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 310/311/ | 310 | 310/311/ | 310 | 1 | 314 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 2 | 314 | 3 | 3 | 52/53/54 | 52/53/54 | 2 | 2 | 2 | 2 | 52/53/54 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 3 | 3 | 3 | 52/54 | 314/327/54/52 | 3 | 314/327/54/52 | 3 | 314/327/54/52 | 94 | 94 |  |  |  | 10598.968 | 16883.752 | 16883.752
| NO. OF SET UPS | 3 | 3 | 3 |  |  |  |  | transfer from 160 | [7 empty] | 33 |  | HG: 33; N: NOT RUN AS PER PLAN; N: PM |  |  |  |  | NOT RUN AS PER PLAN | NOT RUN AS PER PLAN |  |  |  |  | MIR NO 323 NOT RUN | NO OPERATOR | 2 | 2 |  |  | 2 | 2 | 2 |  |  |  | URGENT | URGENT |  | URGENT |  | URGENT |  |  | 0 | 0 | 0 | 10 | 28 | 28 | 0 | 0 | 0
| NO OFOPERATION | 26000 | 26000 | 26000 | 12000 | 12000 | 10500 | 10500 | 3000 | [6 empty] | NOT RUN AS PER PLAN | NOT RUN AS PER PLAN | LOT NO 1 |  |  | 30 | 22000 | 22000 | 22000 | 12000 | 12000 |  | 12000 | 12000 | RP | 14000 | 14000 | 34 | 34 | 25500 | 25500 | 25500 | 25500 | 34 | 1386 MIN | 1386 MIN | 1386 MIN | 900 MIN | 900 MIN | 1386 MIN | 1386 MIN | 1386 MIN | 900 MIN | 900 MIN | 900 MIN | mir 323 | not run | 1237 MIN |  | 1237 MIN |  | 35 ITEMS | 35 ITEMS |  |  |  | 0 | 5172 | 5172
| SECONDARY LOAD | 3600 | 3600 | 7000 | 7000 | 12400 | 12400 | 20000 | 20000 | 20000 | 20000 | 22000 | 22000 | 22000 | 9000 | 2600 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | NOT RUN AS P | NOT RUN AS P | [5 empty] | 20000 | 20000 | 20000 | 20000 | 21500 | 21500 | 21500 | 740 | 740 | 881 | 881 |  |  |  |  | 1270 MIN | 1270 MIN | 1270 MIN | 1270 MIN | 1270 MIN | 1270 MIN | 1273 MIN | 1273 MIN | 1273 MIN | 1273 MIN | 801 MIN | 801 MIN | 801 MIN | 801 MIN |  |  |  | N+N+B+ | N+N+B+ | N+N+B+
| CAL. RUN TIME | S | S | S | S | S | N+S | N+S | S | N | N | N | N | N | N | N+B | N+B | N+B | N+B | HG | N+B | HG | HG | HG | S | S | HG | S | S | N+B | S+HG | S+HG | N+S | N+S | S | S | S | S | N+S | HG | HG | HG | S+N | S+N | HG | HG | HG | S+N | S+N | S+N | N+S | N+B+HG | N+S | N+B+HG | N+S | N+B+HG | N+B | N+B |  |  |  | 148.3108 | 0 | 0
CP04 | PROJECT SECTION (MIR) | N602S-18MT L200X200X16 41077144 | N602S-18MT L200X200X16 41077144 | N602S-18MT L200X200X16 41077144 | N602S-18MT L200X200X16 41077144 | N602S-18MT L200X200X16 41077144 | N602S-18MT L200X200X16 41077144 | N602S-18MT L200X200X16 41077144 | N602S-18MT L200X200X16 41077144 | N602S-18MT L200X200X16 41077144 | N602S-5MT L200X200X16 41077144 | N602S-5MT L200X200X16 41077144 | N602S-5MT L200X200X16 41077144 | N602S-5MT L200X200X16 41077183 | N602S-5MT L200X200X16 41077183 | N602S-5MT L200X200X16 41077183 | N602S-5MT L200X200X16 41077183 | NO LOAD | NO LOAD | NO LOAD | NO LOAD | NO LOAD | NO LOAD | NO LOAD | A621DD-7MT L150X150X18 41077336 | A621DD-7MT L150X150X18 41077336 | A621DD-7MT L150X150X18 41077336 | A621DD-12MT L150X150X18 41077337 | A621DD-7MT L150X150X18 41077338 | A621DD-7MT L150X150X18 41077338 | A621DD-7MT L150X150X18 41077338 | A621DD-7MT L150X150X18 41077338 | A621DD-7MT L150X150X18 41077338 | A621DD-12MT L150X150X18 41077337 | A621DD-12MT L150X150X18 41077338 | A621DD-12MT L150X150X18 41077337 | A621DD-12MT L150X150X18 41077337 | A621DD-12MT L150X150X18 41077337 | A621DD-12MT L150X150X18 41077337 | A621DD-12MT L150X150X18 41077337 | A646DD-2MT LMIX 41077397/398 | A621DD-1MT L200X200X16 41077340 | A621DD-7MT L150X150X18 41077336 | A621DD-7MT L150X150X18 41077336 | A621DD-7MT L150X150X18 41077336 | A621DD-7MT L150X150X18 41077336 | A621DD-7MT L150X150X18 41077336 | A621DD-7MT L150X150X18 41077336 | A621DD-7MT L150X150X18 41077336 | A621DD-7MT L150X150X18 41077336 | A621DD-7MT L150X150X18 41077336 | N602-S-1.5MT L200X200X16 41077542 | A621DD-7MT L150X150X18 41077336 | N602-S-1.5MT L200X200X16 41077542 | N602-S-1.5MT L200X200X16 41077463 | A621DD-3.5MT L MIX 41077341/342 | N602-S-1.5MT L200X200X16 41077542 | A621DD-8MT L150X150X20 41077339 |  |  |  | H250X25(000080135239)(TC922) | H250X25(000080135239)(TC922) | H250X25(000080135239)(TC922) | H250X25(000080135412)(TC922)
| TOTAL WEIGHT | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 51 | 51 | 51 | 51 | 51 | 51 | 51 |  | S: 94; S: 94; HG: 94; B: 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 507 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 54 | 94 | 54 | 54 | 94 | 54 | 94 |  |  |  | 16628 | 16628 | 16628 | 13302.4
| NO. OF SET UPS | [40 empty] | 2 | [16 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
| NO OFOPERATION | [39 empty] | 3 | 600 | [12 empty] | not run | [6 empty] | 0 | 0 | 0 | 0
| SECONDARY LOAD | 3600 | 3600 | 7000 | 7000 | 12400 | 12400 | 20000 | 20000 | 20000 | 20000 | 22000 | 22000 | 22000 | 9000 | 2600 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | NOT RUN AS P | NOT RUN AS P | [5 empty] | 20000 | 20000 | 20000 | 20000 | 21500 | 21500 | 21500 | 740 | 740 | 881 | 881 |  |  |  |  | 1270 MIN | 1270 MIN | 1270 MIN | 1270 MIN | 1270 MIN | 1270 MIN | 1273 MIN | 1273 MIN | 1273 MIN | 1273 MIN | 801 MIN | 801 MIN | 801 MIN | 801 MIN
| CAL. RUN TIME | S+B | S+B | S+B | S+B | S+B | S+B | S+B | S+B | S+B | S | S | S | S | S | S | S | [11 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S+HG | HG | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S |  |  |  | 16.1442 | 16.1442 | 16.1442 | 13.7653 | bar: S to B
CP05 | PROJECT SECTION (MIR) | [57 empty] | H150X10(000080134027)(TC928)H150X10(000080134053)(TC928) | H120X7(000080133812)(TC928) | H150X16(000080133273)(TB901)H200X16(000080133274)(TB901) |  |  |  | H120X8(000080135039)(TC922) | H120X8(000080135039)(TC922)
| TOTAL WEIGHT | [57 empty] | 2637.548 | 5439.4 | 1457.632 |  |  |  | 21402.1331 | 21402.1331
| NO. OF SET UPS | [57 empty] | 5 | 4 | 4 | 0 | 0 | 0 | 18 | 18 | 0
| NO OFOPERATION | [57 empty] | 770 | 1712 | 0 |  |  |  | 0 | 0
| SECONDARY LOAD | [57 empty] | N+ | N+N+B+ |  |  |  |  | B+N+N+B+ | B+N+N+B+
| CAL. RUN TIME | [57 empty] | 39.838 | 72.2317 | 95.46 |  |  |  | 267.6898 | 267.6898
CP06 | PROJECT SECTION (MIR)
TOTAL WEIGHT
NO. OF SET UPS
NO OFOPERATION
SECONDARY LOAD
CAL. RUN TIME
CP07 | PROJECT SECTION (MIR)
TOTAL WEIGHT
NO. OF SET UPS
NO OFOPERATION
SECONDARY LOAD
CAL. RUN TIME
CP08 | PROJECT SECTION (MIR)
TOTAL WEIGHT
NO. OF SET UPS
NO OFOPERATION
SECONDARY LOAD
CAL. RUN TIME
CP09 | PROJECT SECTION (MIR)
TOTAL WEIGHT
NO. OF SET UPS
NO OFOPERATION
SECONDARY LOAD
CAL. RUN TIME
CP10 | PROJECT SECTION (MIR)
TOTAL WEIGHT
NO. OF SET UPS
NO OFOPERATION
SECONDARY LOAD
CAL. RUN TIME
CD22 | PROJECT SECTION (MIR)
TOTAL WEIGHT
NO. OF SET UPS
NO OFOPERATION
SECONDARY LOAD
CAL. RUN TIME
plan compliances
LOAD/LOT.
PAB-44
plan compliances
LOAD/LOT.
WELDED
plan compliances
LOAD/LOT.
HEEL CUTTING (by mechanical mc)
plan compliances
LOAD/LOT.
BAND SAW
GRINDING/HG/ GAS NOTCHING
PLANNED OUTPUT
ACTUAL OUTPUT.
% PERFORMANCE WITH RESPECT TO OUTPUT
NO OF MACINE PLAN
NO OF MACHINE DID NOT RUN AS PER PLAN
% PLAN COMPLIENCE
NET HANDING OVER
SHIFT INCHARGE
Machine compliance report
| CP01 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| CP02 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| CP03 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| CP04 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| CP05 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| CP06 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| DB363 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| SUM | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 6 | 5 | 4 | 5 | 6 | 6 | 6 | 7 | 4 | 5 | 7 | 6 | 5 | 5 | 5 | 7 | 6 | 6 | 6 | 4 | 7 | 6 | 7 | 7 | 6 | 5 | 7 | 6 | 7 | 7 | 7 | 6 | 7 | 7 | 7 | 6 | 6 | 4 | 6 | 6 | 6 | 7 | 7 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| % | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 85.7143 | 71.4286 | 57.1429 | 71.4286 | 85.7143 | 85.7143 | 85.7143 | 100 | 57.1429 | 71.4286 | 100 | 85.7143 | 71.4286 | 71.4286 | 71.4286 | 100 | 85.7143 | 85.7143 | 85.7143 | 57.1429 | 100 | 85.7143 | 100 | 100 | 85.7143 | 71.4286 | 100 | 85.7143 | 100 | 100 | 100 | 85.7143 | 100 | 100 | 100 | 85.7143 | 85.7143 | 57.1429 | 85.7143 | 85.7143 | 85.7143 | 100 | 100 | 85.7143 | 85.7143 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
88.9163
JULY UP TO DATE