## Plan
| ISO : F3.5 | [58 empty] | 43844.6605
| DATE | 2017-07-01 |  |  | 2017-07-02 |  |  | 2017-07-03 |  |  | 2017-07-04 |  |  | 2017-07-05 |  |  | 2017-07-06 |  |  | 2017-07-07 |  |  | 2017-07-08 |  |  | 2017-07-09 |  |  | 2017-07-10 |  |  | 2017-07-11 |  |  | 2017-07-12 |  |  | 2017-07-13 |  |  | 2017-07-14 |  |  | 2017-07-15 |  |  | 2017-07-16 |  |  | 2017-07-17 |  |  | 2017-07-18 |  |  | 2017-07-19 |  |  |  | 2020-01-14 |  |  | 2020-01-15 |  |  | 2020-01-16 |  | 2017-07-23
| SHIFT | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D | B | C | D
CD-22 | PROJECT SECTION (MIR) | C762A-15MT HT60X60X5 41076933 | C762A-15MT HT60X60X5 41076933 | C762A-15MT HT60X60X5 41076933 | C762A-1.5MT HT75X75X6 41077115 | C792A-13MT MS70X70X5 41077128 | C792A-13MT MS70X70X5 41077128 | C792A-13MT MS70X70X5 41077128 | B7591D-0.5MT L55X55X4 41076971 | C639CT-4MT L60X60X5 41076842 | C639CT-4MT L60X60X5 41076842 | C639T-5.2MT L50X50X5 41076841 | C762A-26.MT L50X50X5 41076939 | C762A-26.MT L50X50X5 41076939 | C762A-26.MT L50X50X5 41076939 | C762A-26.MT L50X50X5 41076939 | C762A-26.MT L50X50X5 41076939 | C762A-26.MT L50X50X5 41076939 | C762A-12MT L50X50X5 41077119 | C762A-12MT L50X50X5 41077119 | C762A-12MT L50X50X5 41077119 | C762A-12MT L50X50X5 41077119 | C762A-12MT L50X50X5 41077119 | C762A-12MT L50X50X5 41077119 | C639CT-4MT L60X60X5 41076842 | C639CT-4MT L60X60X5 41076842 | C639CT-1MT L MIX 41077045/230/231 | C762A-27MT L50X50X5 41077149 | C762A-27MT L50X50X5 41077149 | C762A-24MT L50X50X5 41076941 | C762A-24MT L50X50X5 41076941 | C762A-24MT L50X50X5 41076941 | C762A-24MT L50X50X5 41076941 | C639CT-1MT L MIX 41077045/230/231 | N602-7MT L55X55X5 41077256 | N602-7MT L55X55X5 41077256 | N602-7MT L55X55X5 41077256 | N602-1MT L50X50X5 41077316 | C762A-20MT L70X70X5 41077488 | C762A-20MT L70X70X5 41077488 | C762A-20MT L70X70X5 41077488 | C762A-20MT L70X70X5 41077488 | C762A-20MT L70X70X5 41077488 | C762A-22MT L65X65X5 41077232 | C762A-22MT L65X65X5 41077232 | C762A-22MT L65X65X5 41077232 | C762A-22MT L65X65X5 41077232 | C762A-1.5MT L60X60X5 41077548 | C762A-1.5MT L60X60X5 41077548 | C762A-21MT L70X70X5 41077547 | C762A-21MT L70X70X5 41077547 | C762A-21MT L70X70X5 41077547 | C762A-21MT L70X70X5 41077547 | C762A-21MT L70X70X5 41077547 | C762A-21MT L70X70X5 41077547 | C762A-21MT L70X70X5 41077547 | C762A-6.5MT L70X70X5 41077538 | C762A-8.5MT L50X50X5 41077624 | M45X5(000080134527)(0S806) | M50X4(000080133309)(TC922) | M55X4(000080134532)(0S806) | M55X4(000080134532)(0S806) | M65X4(000080134304)(TB901)
| TOTAL WEIGHT | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 301 | 317 | 317 | 317 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 317 | 317 | 314 | 2 | 2 | 2 | 2 | 2 | 2 | 314 | 52/53/54 | 52/53/54 | 52/53/54 | 53/54 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 1044.46 | 3585.928 | 4882.496 | 3314.468 | 120.02
| NO. OF SET UPS | [8 empty] | 35 | 35 | [13 empty] | 35 | 35 | [12 empty] | 10700 MM LENGTH | 10700 MM LENGTH | 10700 MM LENGTH | 10700 MM LENGTH | 10700 MM LENGTH | 9600 | 9600 | 9600 | 9600 |  |  |  |  | BD | BD | RE | RE | RE | 1700 |  | 16 | 28 | 44 | 36 | 5 | 0 | 0 | 0 | 0
| NO OFOPERATION |  |  |  | 3000 | 3600 | 3600 | 3600 |  |  |  |  | N | N | N | N | N | N | [8 empty] | Not run as per paln | 102 plan | 102 plan | 14 | 14 | 14 | 14 |  | 118 | 118 | 118 |  | DIRECT ISSUE | DIRECT ISSUE | DIRECT ISSUE | DIRECT ISSUE | DIRECT ISSUE | 1067 MIN | 1067 MIN | 1067 MIN | 1067 MIN | 885 MIN | 885 MIN | 886 MIN | 886 MIN | 886 MIN | 886 MIN | 886 MIN | 886 MIN | 886 MIN |  | 571 MIN | 1798 | 0 | 4128 | 2960 | 47
| SECONDARY LOAD | [57 empty] | N+ | N+ | B+W+N+ | N+ | B+N+
| CAL. RUN TIME | n+s | n+s | n+s | S | N | N | N | S | N+S | N+S | N+B | N | N | N | N | N | N | N+S | N+S | N+S | N+S | N+S | N+S | N+S | N+S | N | N+B | N+B | N+S | N+S | N+S | N+S | N | N+B | N+B | N+B | N | N | N | N | N | N | N | N | N | N | HG | HG | N+S | N+S | N+S | N+S | N+S | N+S | N+S | N | N+S | 0 | 508.1581 | 518.0252 | 518.0252 | 0
CD-14 | PROJECT SECTION (MIR) | N712A-2MT L40X40X4 41077063 | C762A-24MT L50X50X5 41076935 | C762A-24MT L50X50X5 41076935 | C762A-24MT L50X50X5 41076935 | C762A-24MT L50X50X5 41076935 | C762A-24MT L50X50X5 41076935 | C762A-24MT L50X50X5 41076935 | C762A-24MT L50X50X5 41076935 | C639LM-5MT L50X50X5 41077044 | C639LM-5MT L50X50X5 41077044 | C639LM-5MT L50X50X5 41077044 | C762A-25MT L50X50X5 41076943 | C762A-25MT L50X50X5 41076943 | C762A-25MT L50X50X5 41076943 | C762A-25MT L50X50X5 41076943 | C762A-25MT L50X50X5 41076943 | C762A-25MT L50X50X5 41076943 | C762A-25MT L50X50X5 41076943 | C762A-25MT L50X50X5 41076943 | C762A-16MT L50X50X5 41077118 | C762A-16MT L50X50X5 41077118 | C762A-16MT L50X50X5 41077118 | C762A-16MT L50X50X5 41077118 | A623S-0.6MT L45X45X4 41077164 | C762A-24MT L50X50X5 41076941 | C762A-24MT L50X50X5 41076941 | C762A-24MT L50X50X5 41076941 | C762A-24MT L50X50X5 41076941 | C762A-27MT L50X50X5 41077149 | C762A-27MT L50X50X5 41077149 | C762A-27MT L50X50X5 41077149 | C762A-27MT L50X50X5 41077149 | C762A-27MT L50X50X5 41077149 | C762A-27MT L50X50X5 41077149 | C762A-27MT L50X50X5 41077149 | C762A-12MT L50X50X5 41077223 | C762A-12MT L50X50X5 41077223 | C762A-12MT L50X50X5 41077223 | C762A-13MT L50X50X5 41077224 | C762A-13MT L50X50X5 41077224 | C762A-6MT L50X50X5 41077225 | C762A-6MT L50X50X5 41077225 | C762A-15MT L50X50X5 41077549 | C762A-15MT L50X50X5 41077549 | C762A-15MT L50X50X5 41077549 | C639-8MT L45X45X5 41077510 | C639-8MT L45X45X5 41077510 | C639-8MT L45X45X5 41077510 | C639-8MT L45X45X5 41077510 | C639/C762A-1MT L65X5(41077455) L50X6(41077512) | C639/C762A-1MT L65X5(41077455) L50X6(41077512) | C639/C762A-1MT L65X5(41077455) L50X6(41077512) | A621DD-3.5MT L45X45X4 41077584 | A621DD-3.5MT L45X45X4 41077584 | A621DD-3.5MT L45X45X4 41077584 | C762A-10MT L50X50X5 41077612 | C762A-10MT L50X50X5 41077612 | H45X4(000080135069)(TC922)
| TOTAL WEIGHT | 300 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 314 | 314 | 314 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 37 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 310 | 310 | 310 | 310 | 4/331 | 4/331 | 4/331 | 84 | 84 | 84 | 2,3 | 2,3 | 9664.452
| NO. OF SET UPS | 174 | [23 empty] | 160 plan | 160 plan | 160 plan | 160 plan | 6 shift | 6 shift | 6 shift | 6 shift | 6 shift | 6 shift | 6 shift | [17 empty] | 205 | 205 | 205 |  |  | 142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| NO OFOPERATION | [57 empty] | 0
| SECONDARY LOAD |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | [11 empty] | 1293 MIN | 1293 MIN | 1293 MIN | 1293 MIN |  | 14 | 14 | 14 | 14 |  |  |  | BD/2 | no operator | DB/2 |  | 3 | 3 | 3 | 3 | 3 |  |  | 1778 MIN | 1778 MIN | 1778 MIN | 119 | 119 | 119 | 119 | [6 empty] | 761 MIN | 761 MIN | N+N+B+
| CAL. RUN TIME | N | N | N | N | N | N | N | N | N+B+ | N+B+ | N+B+ | NB+ | NB+ | NB+ | NB+ | NB+ | NB+ | NB+ | NB+ | S | S | S | S | N+S | N+S | N+S | N+S | N+S | N+B | N+B | N+B | N+B | N+B |  | N+B | N+B | N+B | N+B | N+B | N+B | N | N | N | N | N | N+B | N+B | N+B | N+B | N+HG | N+HG | N+HG | N+B | N+B | N+B | N+B | N+B | 1896.44
CP-02 | PROJECT SECTION (MIR) | C762A-8MT H75X75X5 41077114 | C762A-1.5MT L100X100X6 41077898 | C762A-8MT H75X75X5 41077114 | C762A-8MT H75X75X5 41077114 | C762A-21MT MS70X70X5 41077093 | C762A-21MT MS70X70X5 41077093 | C762A-8MT H75X75X5 41077114 | C639/B759-2MT L MIX 41076845/965//972/964/834 | C639CT-5MT LMIX 41076828/29/082 | C762A-1.5MT HT75X75X6 41077115 | C639/B759-2MT L MIX 41076845/965//972/964/834 | C639CT-5MT LMIX 41076828/29/082 | C639CT-3MT L MIX 41076831/832/833/839/830/043 | C762A-24MT L70X70X5 41077126 | C762A-24MT L70X70X5 41077126 | C762A-24MT L70X70X5 41077126 | C762A-24MT L70X70X5 41077126 | C762A-1MT L80X80X6 41077156 | C639CT-8MT L MIX 41076828/29/31/32/33/39/043 | C639CT-8MT L MIX 41076828/29/31/32/33/39/043 | C762A-6MT L70X70X5 41077126 | C762A-6MT L70X70X5 41077126 | C762A-1.5MT L75X75X6 41077148 | C762A-11MT L80X80X6 41077185 | C762A-11MT L80X80X6 41077185 | C762A-1.5MT L100X100X6 41077167 | C762A-10MT L90X90X6 41077189 | N602Q/S-4MT LMIX 41077262/197/833 | C762A-1.5MT L75X75X6 41077148 | C762A-12MT L90X90X6 41077188 | C762A-12MT L90X90X6 41077188 | C762A-12MT L90X90X6 41077188 | ITEM NOC762A-23,24,25,32,33 L70X70X5 41077414 LENGTH 10700/800PCS | ITEM NOC762A-23,24,25,32,33 L70X70X5 41077414 LENGTH 10700/800PCS | ITEM NOC762A-23,24,25,32,33 L70X70X5 41077414 LENGTH 10700/800PCS | ITEM NOC762A-23,24,25,32,33 L70X70X5 41077414 LENGTH 10700/800PCS | ITEM NOC762A-23,24,25,32,33 L70X70X5 41077414 LENGTH 10700/800PCS | ITEM NOC762A-23,24,25,32,33 L70X70X5 41077414 LENGTH 10700/800PCS | ITEM NOC762A-23,24,25,32,33 L70X70X5 41077414 LENGTH 10700/800PCS | C762A-21MT L70X70X5 41077489 | C762A-21MT L70X70X5 41077489 | C762A-21MT L70X70X5 41077489 | C762A-25MT L70X70X5 41077529 | C762A-25MT L70X70X5 41077529 | C762A-25MT L70X70X5 41077529 | C762A-14MT L75X75X5 41077244 | C762A-14MT L75X75X5 41077244 | C762A-21MT L70X70X5 41077533 | C762A-14MT L75X75X5 41077244 | C762A-15MT L70X70X5 41077563 | C762A-15MT L70X70X5 41077563 | C762A-21MT L70X70X5 41077533 | C762A-21MT L70X70X5 41077533 | C762A-1MT L70X70X5 41077579 | C762A-21MT L70X70X5 41077533 | C762A-1MT L70X70X5 41077579 | C762A-21MT L70X70X5 41077533 |  |  |  | H100X7(000080135451)(TC928) | H100X7(000080135451)(TC928) | H75X5(000080135494)(TC922)M60X4(000080135251)(TC922)M60X4(000080135252)(TC928)
| TOTAL WEIGHT | 1 | 6 | 1 | 1 | 1 | 1 | 1 | 301/317 | 317 | 1 | 301/317 | 317 | 317 | 2 | 2 | 2 | 2 | 1 | 317 | 317 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 54/52 | 2 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 3 | 3 | 4 | 4 | 2,3 | 4 | 2,3 | 4 |  |  |  | 12329.1361 | 12329.1361 | 3375.216
| NO. OF SET UPS | [9 empty] | transfer from 160 | [8 empty] | 41 | 41 |  |  | NOT RUN AS P | [5 empty] | rp |  |  |  | NOT RUN(T3 ROUT SHHET RUN) | DIRECT UNLOAD | DIRECT UNLOAD | DIRECT UNLOAD | DIRECT UNLOAD | DIRECT UNLOAD | DIRECT UNLOAD | DIRECT UNLOAD | DIRECT UNLOAD | DIRECT UNLOAD | 4 | 4 | 4 | [12 empty] | 0 | 0 | 0 | 27 | 27 | 11 | 0 | 0 | 0
| NO OFOPERATION | 11000 |  | 11000 | 11000 | 10500 | 10500 | 11000 |  |  | 3000 |  |  |  | BD | BD | BD | BD | 5600 | BD |  |  |  | 3500 | 10000 | 10000 | 7200 | 2600 |  | 3500 | 14000 | 14000 | 14000 | 1715 MIN | 1715 MIN | 1715 MIN | 1715 MIN | 1715 MIN | 1715 MIN | 1715 MIN |  |  |  | 1270 MIN | 1270 MIN | 1270 MIN | 537 MIN | 537 MIN | 885 MIN | 537 MIN |  |  | 885 MIN | 885 MIN | 3200 | 885 MIN | 3200 | 885 MIN |  |  |  | 10928 | 10928 | 144
| SECONDARY LOAD | 3600 | 3600 | 7000 | 7000 | 12400 | 12400 | 20000 | 20000 | 20000 | 20000 | 22000 | 22000 | 22000 | 9000 | 2600 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | NOT RUN AS P | NOT RUN AS P | [5 empty] | 20000 | 20000 | 20000 | 20000 | 21500 | 21500 | 21500 | 740 | 740 | 881 | 881 |  |  |  |  | 1270 MIN | 1270 MIN | 1270 MIN | 1270 MIN | 1270 MIN | 1270 MIN | 1273 MIN | 1273 MIN | 1273 MIN | 1273 MIN | 801 MIN | 801 MIN | 801 MIN | 801 MIN |  |  |  | N+ | N+ | N+
| CAL. RUN TIME | N+B+HG | CLAETS | N+B+HG | N+B+HG | N+S | N+S | N+B+HG | N+B | N+W | S | N+B | N+W | N | N+ | N+ | N+ | N+ | HG | N | N | N | N | S | S | S | HG | B | N+B | S | B+S | B+S | B+S | N | N | N | N | N | N | N | N | N | N | N+S | N+S | N+S | N | N | N | N | N+B | N+B | N | N | HG | N | HG | N |  |  |  | 0 | 0 | 183.297
CP-03 | PROJECT SECTION (MIR) | C762A-14MT MS75X75X5 41076945 | C762A-14MT MS75X75X5 41076945 | C762A-8MT H80X80X6 41077141 | C762A-8MT H80X80X6 41077141 | C762A-40MT H130X130X12 41077107 | C762A-40MT H130X130X12 41077107 | C762A-58MT L130X130X10 41077055 | C762A-58MT L130X130X10 41077055 | C762A-58MT L130X130X10 41077055 | C762A-58MT L130X130X10 41077055 | C762A-6MT L110X110X8 41077089 | C762A-6MT L110X110X8 41077089 | C762A-6MT L110X110X8 41077089 | C762A-19MT L130X130X10 41077057 | C762A-10MT L90X90X6 41077116 | C762A-40MT L130X130X12 41077166 | C762A-40MT L130X130X12 41077166 | C762A-40MT L130X130X12 41077177 | C762A-40MT L130X130X12 41077177 | C762A-40MT L130X130X12 41077177 | C762A-40MT L130X130X12 41077177 | C762A-12MT L120X120X10 41077165/176 | C762A-12MT L120X120X10 41077165/176 | C762A-12MT L120X120X10 41077165/176 | C762A-12MT L120X120X10 41077165/176 | C762A-12MT L120X120X10 41077165/176 | C762A-12MT L120X120X10 41077165/176 | C762A-12MT L120X120X10 41077165/176 | C762A-58MT L130X130X10 41077170 | C762A-58MT L130X130X10 41077170 | C762A-58MT L130X130X10 41077170 | C762A-58MT L130X130X10 41077170 | C762A-58MT L130X130X10 41077220 | C762A-58MT L130X130X10 41077220 | C762A-58MT L130X130X10 41077220 | C762A-28MT L120X120X10 41077218 | C762A-28MT L120X120X10 41077218 | C762A-28MT L120X120X10 41077219 | C762A-28MT L120X120X10 41077219 | C762A-19MT L130X130X10 41077283 | C762A-22MT L70X70X5 41077490 | C762A-22MT L70X70X5 41077490 | C762A-22MT L70X70X5 41077490 | C762A-25MT L70X70X5 41077530 | C762A-25MT L70X70X5 41077530 | C762A-25MT L70X70X5 41077530 | C762A-25MT L70X70X5 41077530 | C762A-25MT L70X70X5 41077530 | C762A-25MT L70X70X5 41077530 | C762A-24MT L70X70X5 41077536 | C762A-24MT L70X70X5 41077536 | C762A-24MT L70X70X5 41077536 | C762A-24MT L70X70X5 41077536 | C762A-15MT L80X80X6 41077572 | C762A-15MT L80X80X6 41077572 | C762A-15MT L80X80X6 41077573 | C762A-15MT L80X80X6 41077573 |  |  |  | H110X8(000080135173)(TC922) | H110X8(000080135173)(TC922) | H110X8(000080135173)(TC922)
| TOTAL WEIGHT | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 8 | 8 | 8 | 8 | 8 | 8 | 8,9 | 8,9 | 8,9 | 8,9 | 8,9 | 8,9 | 8,9 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 3 |  |  |  | 24582.518 | 24582.518 | 24582.518
| NO. OF SET UPS | [10 empty] | 2 | 2 | 2 |  |  | NOT RUN AS PER PLAN RUN T3 77116 | [12 empty] | 3 | 3 | BD | 3 | 1553 MIN | 3 | 3 | 1 | 1 | 1 | 1 |  | 3 | 3 | 3 | [10 empty] | DIRECT ISSUE | DIRECT ISSUE | DIRECT ISSUE | DIRECT ISSUE | 0 | 0 | 0 | 22 | 22 | 22 | 0 | 0 | 0
| NO OFOPERATION | 10000 | 10000 | 10000 | 10000 | 10000 | 7500 | 7500 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 6400 | 2600 |  | 3600 | 3 | 3 | 3 | 16000 | 16000 | 16000 | [5 empty] | 1772 MIN | 1772 MIN | 1772 MIN | 1772 MIN | 1772 MIN | 34 | 27400 | 27400 | 27400 | 27400 | 27400 | 395 MIN |  |  |  | 2 | 1 | 2 | 2 | 2 | 840 MIN | 840 MIN | 840 MIN | 55 ITEM | 55 ITEM |  | 55 ITEM |  |  |  |  | 0 | 0 | 0
| SECONDARY LOAD | 3600 | 3600 | 7000 | 7000 | 12400 | 12400 | 20000 | 20000 | 20000 | 20000 | 22000 | 22000 | 22000 | 9000 | 2600 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | NOT RUN AS P | NOT RUN AS P | [5 empty] | 20000 | 20000 | 20000 | 20000 | 21500 | 21500 | 21500 | 740 | 740 | 881 | 881 |  |  |  |  | 1270 MIN | 1270 MIN | 1270 MIN | 1270 MIN | 1270 MIN | 1270 MIN | 1273 MIN | 1273 MIN | 1273 MIN | 1273 MIN | 801 MIN | 801 MIN | 801 MIN | 801 MIN |  |  |  | B+N+N+B+ | B+N+N+B+ | B+N+N+B+
| CAL. RUN TIME | S | S | S | S | S | S | S | S | S | S | HG | HG | HG | S | B | STUB | STUB | STUB | STUB | STUB | STUB | STUB CLEATS | STUB CLEATS | STUB CLEATS | STUB CLEATS | STUB CLEATS | STUB CLEATS | STUB CLEATS | S | S | S | S | S | S | S | B | B | B | B | S | N+S | N+S | N+S | S+N | S+N | S+N | S+N | S+N | S+N | N+S | N+S | N+S | N+S | B | B | B | B |  |  |  | 330.5366 | 330.5366 | 330.5366
CP-04 | PROJECT SECTION (MIR) | C762A-12MT L90X90X6 41077117 | C762A-12MT L90X90X6 41077117 | C762A-12MT L90X90X6 41077117 | C762A-19MT L130X130X10 41077056 | C762A-19MT L130X130X10 41077056 | C762A-14MT L120X120X10 41076901 | C762A-14MT L120X120X10 41076743 | C762A-58MT L130X130X10 41077054 | C762A-58MT L130X130X10 41077054 | C762A-58MT L130X130X10 41077054 | C762A-58MT L130X130X10 41077054 | C762A-58MT L130X130X10 41077054 | C762A-58MT L130X130X10 41077054 | C762A-58MT L130X130X10 41077054 | C762A-15MT L80X80X6 41077140 | C762A-10MT L90X90X6 41077116 | E701OE-1MT L65X6(77287) L75X8(77288) | C639-11.5MT L110X110X8 41077071 | C762A-16MT L80X80X6 41077184 | C762A-16MT L80X80X6 41077184 | C762A-16MT L80X80X6 41077184 | C762A-23MT L80X80X6 41077157 | C762A-23MT L80X80X6 41077157 | C762A-23MT L80X80X6 41077157 | N602Q/S-4MT LMIX 41077245/246/262 | C762A-7MT L75X75X5 41077195 | C762A-1MT L75X75X5 41077196 | C762A-15MT L80X80X6 41077187 | C762A-15MT L80X80X6 41077187 | ITEM NOC762A-26,27,34,35 L70X70X5 41077414 LENGTH 9850/800PCS | ITEM NOC762A-26,27,34,35 L70X70X5 41077414 LENGTH 9850/800PCS | ITEM NOC762A-26,27,34,35 L70X70X5 41077414 LENGTH 9850/800PCS | ITEM NOC762A-26,27,34,35 L70X70X5 41077414 LENGTH 9850/800PCS | ITEM NOC762A-26,27,34,35 L70X70X5 41077414 LENGTH 9850/800PCS | N602-3MT L70X5,90X6 41077321,22,23,24,20 | C762A-34MT L110X110X8 41077390 | C762A-34MT L110X110X8 41077390 | C762A-34MT L110X110X8 41077390 | C762A-34MT L110X110X8 41077390 | N602/C762A-34MT L110X110X8 41077390/246 | N602/C762A-9 MT L110X110X8 41077399/370 | C762A-20MT L90X90X6 41077235 | C762A-20MT L90X90X6 41077235 | C762A-2MT L90X90X6 41077236 | C762A-1.2MT L75X75X6 41077234 | C762A-1.2MT L100X100X6 41077217 | C762A-15MT L80X80X6 41077335 | C762A-15MT L80X80X6 41077335 | C762A-15MT L80X80X6 41077335/234 | C762A-21MT L70X70X5 41077534 | C762A-21MT L70X70X5 41077534 | C762A-21MT L70X70X5 41077534/234 | N602-6MT L65X65X5 41077565/566 | N602-6MT L65X65X5 41077565/566 | C762A-5MT L70X70X5 41077567/568/566 | N602-6MT L65X65X5 41077565/566 | C762A-5MT L70X70X5 41077567/568 |  |  |  | H100X7(000080135453)(TC922)M80X5(000080135308)(TC922) | H100X7(000080135453)(TC922) | M75X5(000080135304)(TC922)M80X5(000080135308)(TC922)
| TOTAL WEIGHT | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 6 | 2 | 2 | 2 | 2 | 2 | 2 | 54/52 | 3 | 3 | 3 | 3 | LOT NO 2 | LOT NO 2 | LOT NO 2 | LOT NO 2 | LOT NO 2 | 52/53/54 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 52/54 | 52/54 | 2,3 | 52/54 | 2,3 |  |  |  | 22186.376 | 19317.096 | 5283.544
| NO. OF SET UPS | [6 empty] | PL IN SHOP | [8 empty] | RUN ON CP06 | RAILWAYS | 412 MIN | 11600 | 11600 | 11600 | RUNNING ON CP04 | RUNNING ON CP04 | [6 empty] | NOT RUN AS PELAN | DIRECT UNLOAD | DIRECT UNLOAD | DIRECT UNLOAD | DIRECT UNLOAD | T4 PLAN SHIFTED |  |  |  | NO OPERATOR |  | MIR NO 370 NOT RUN |  |  | 5 | NOT RUN |  |  |  | mir no 234 not run | [8 empty] | 0 | 0 | 0 | 26 | 20 | 10 | 0 | 0 | 0
| NO OFOPERATION | 10000 | 10000 | 10000 | 10000 | 10000 | 7500 | 7500 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 6400 | 2600 |  | 3600 | 3 | 3 | 3 | 16000 | 16000 | 16000 | [5 empty] | 1772 MIN | 1772 MIN | 1772 MIN | 1772 MIN | 1772 MIN | 34 | 27400 | 27400 | 27400 | 27400 | 27400 | 395 MIN |  |  |  | 2 | 1 | 2 | 2 | 2 | 840 MIN | 840 MIN | 840 MIN | 55 ITEM | 55 ITEM |  | 55 ITEM | no operator |  |  |  | 0 | 0 | 0
| SECONDARY LOAD | 3600 | 3600 | 7000 | 7000 | 12400 | 12400 | 20000 | 20000 | 20000 | 20000 | 22000 | 22000 | 22000 | 9000 | 2600 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | NOT RUN AS P | NOT RUN AS P | [5 empty] | 20000 | 20000 | 20000 | 20000 | 21500 | 21500 | 21500 | 740 | 740 | 881 | 881 |  |  |  |  | 1270 MIN | 1270 MIN | 1270 MIN | 1270 MIN | 1270 MIN | 1270 MIN | 1273 MIN | 1273 MIN | 1273 MIN | 1273 MIN | 801 MIN | 801 MIN | 801 MIN | 801 MIN |  |  |  | B+N+N+B+ | B+N+N+B+ | N+
| CAL. RUN TIME | S | S | S | S | S | B | B | S | S | S | S | S | S | S | B | B | B | S | B | B | B | S | S | S | N+B | B+S | HG | B+S | B+S | N | N | N | N | N | N+S | S | S | S | S | S | S | B | B | S | S | HG | B | B | B | N | N | N | N+B | N+B | B | N+B | B |  |  |  | 473.4433 | 348.112 | 233.7272
CP-05 | PROJECT SECTION (MIR) | C762A-34MT H110X110X8 41077088 | C762A-34MT H110X110X8 41077088 | C762A-34MT H110X110X8 41077088 | C762A-6MT L120X120X10 41077105 | C762A-6MT L120X120X10 41077105 | C762A-21MT MS70X70X5 41077093 | C762A-21MT MS70X70X5 41077093 | C762A-1.5MT HT75X75X6 41077115 | C762A-23MT L70X70X5 41077130 | C762A-23MT L70X70X5 41077130 | C762A-23MT L70X70X5 41077130 | C762A-23MT L70X70X5 41077130 | C762A-23MT L70X70X5 41077130 | C762A-23MT L70X70X5 41077130 | C6392T-2MT L MIX 41077046/083/084 | C639-1MT L65X65X6 41077047 | /C762/C6392T-2MT L MIX 41077046/083/084/154 | C639-1MT L65X65X6 41077047 | C762A-1MT L80X80X6 41077156 | N712A-1.5+N602-3 MT L MIX 41077058/059/77070 | C762A-6MT L110X110X8 41077090 | C762A-6MT L110X110X8 41077090 | C762A-6MT L110X110X8 41077090 | C762A-16MT L110X110X8 41077145 | C762A-16MT L110X110X8 41077145 | C762A-1.2MT L75X75X6 41077197 | C762A-16MT L110X110X8 41077145 | C762A-16MT L110X110X8 41077145 | N712A-1.5+N602-3 MT L MIX 41077058/059/77070 | C762A-4MT L60X60X5 41077284/285 | C762A-1.2MT L75X6 41077148 | N602-3MT L70X5,90X6 41077321,22,23,24,20 | N602-3MT L70X5,90X6 41077321,22,23,24,20 | C762A-34MT L110X110X8 41077391 | C762A-34MT L110X110X8 41077391 | C762A-34MT L110X110X8 41077391 | C762A-34MT L110X110X8 41077391 | N602-3MT L70X5,90X6 41077321,22,23,24,20 | C762A-6.2MT L110X110X8 41077334 | C762A-6.2MT L110X110X8 41077334 | C762A-6.2MT L110X110X8 41077334 | C762A-20MT L70X70X5 41077532 | C762A-20MT L70X70X5 41077532 | C762A-6.2MT L110X110X8 41077392 | C762A-6.2MT L110X110X8 41077392 | C762A-6.2MT L110X110X8 41077392 | C762A-20MT L70X70X5 41077532 | C762A-20MT L70X70X5 41077532 | C762A-20MT L70X70X5 41077532 | N602-2.8MT L MIX 41077322/323/370 | N602/C639-3MT LMIX 41077539/541/543/446/462 | C762A-24MT L70X70X5 41077545 | N602/C639-3MT LMIX 41077539/541/543/446/462/323 | C762A-24MT L70X70X5 41077545 | N602/C639-3MT LMIX 41077539/541/543/446/462/323 | A621DD-4MT L MIX 41077440/479 | A621DD-4MT L MIX 41077440/479 |  |  |  | H110X8(000080135013)(TC922) | H100X8(000080134762)(0S806) | H100X8(000080134762)(0S806)
| TOTAL WEIGHT | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 310/311/ | 310 | 310/311/ | 310 | 1 | 314 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 2 | 314 | 3 | 3 | 52/53/54 | 52/53/54 | 2 | 2 | 2 | 2 | 52/53/54 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 3 | 3 | 3 | 52/54 | 314/327/54/52 | 3 | 314/327/54/52 | 3 | 314/327/54/52 | 94 | 94 |  |  |  | 10598.968 | 16883.752 | 16883.752
| NO. OF SET UPS | 3 | 3 | 3 |  |  |  |  | transfer from 160 | [7 empty] | 33 |  | HG: 33; N: NOT RUN AS PER PLAN; N: PM |  |  |  |  | NOT RUN AS PER PLAN | NOT RUN AS PER PLAN |  |  |  |  | MIR NO 323 NOT RUN | NO OPERATOR | 2 | 2 |  |  | 2 | 2 | 2 |  |  |  | URGENT | URGENT |  | URGENT |  | URGENT |  |  | 0 | 0 | 0 | 10 | 28 | 28 | 0 | 0 | 0
| NO OFOPERATION | 26000 | 26000 | 26000 | 12000 | 12000 | 10500 | 10500 | 3000 | [6 empty] | NOT RUN AS PER PLAN | NOT RUN AS PER PLAN | LOT NO 1 |  |  | 30 | 22000 | 22000 | 22000 | 12000 | 12000 |  | 12000 | 12000 | RP | 14000 | 14000 | 34 | 34 | 25500 | 25500 | 25500 | 25500 | 34 | 1386 MIN | 1386 MIN | 1386 MIN | 900 MIN | 900 MIN | 1386 MIN | 1386 MIN | 1386 MIN | 900 MIN | 900 MIN | 900 MIN | mir 323 | not run | 1237 MIN |  | 1237 MIN |  | 35 ITEMS | 35 ITEMS |  |  |  | 0 | 5172 | 5172
| SECONDARY LOAD | 3600 | 3600 | 7000 | 7000 | 12400 | 12400 | 20000 | 20000 | 20000 | 20000 | 22000 | 22000 | 22000 | 9000 | 2600 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | NOT RUN AS P | NOT RUN AS P | [5 empty] | 20000 | 20000 | 20000 | 20000 | 21500 | 21500 | 21500 | 740 | 740 | 881 | 881 |  |  |  |  | 1270 MIN | 1270 MIN | 1270 MIN | 1270 MIN | 1270 MIN | 1270 MIN | 1273 MIN | 1273 MIN | 1273 MIN | 1273 MIN | 801 MIN | 801 MIN | 801 MIN | 801 MIN |  |  |  | N+N+B+ | N+N+B+ | N+N+B+
| CAL. RUN TIME | S | S | S | S | S | N+S | N+S | S | N | N | N | N | N | N | N+B | N+B | N+B | N+B | HG | N+B | HG | HG | HG | S | S | HG | S | S | N+B | S+HG | S+HG | N+S | N+S | S | S | S | S | N+S | HG | HG | HG | S+N | S+N | HG | HG | HG | S+N | S+N | S+N | N+S | N+B+HG | N+S | N+B+HG | N+S | N+B+HG | N+B | N+B |  |  |  | 148.3108 | 0 | 0
CP-08 | PROJECT SECTION (MIR) | N602S-18MT L200X200X16 41077144 | N602S-18MT L200X200X16 41077144 | N602S-18MT L200X200X16 41077144 | N602S-18MT L200X200X16 41077144 | N602S-18MT L200X200X16 41077144 | N602S-18MT L200X200X16 41077144 | N602S-18MT L200X200X16 41077144 | N602S-18MT L200X200X16 41077144 | N602S-18MT L200X200X16 41077144 | N602S-5MT L200X200X16 41077144 | N602S-5MT L200X200X16 41077144 | N602S-5MT L200X200X16 41077144 | N602S-5MT L200X200X16 41077183 | N602S-5MT L200X200X16 41077183 | N602S-5MT L200X200X16 41077183 | N602S-5MT L200X200X16 41077183 | NO LOAD | NO LOAD | NO LOAD | NO LOAD | NO LOAD | NO LOAD | NO LOAD | A621DD-7MT L150X150X18 41077336 | A621DD-7MT L150X150X18 41077336 | A621DD-7MT L150X150X18 41077336 | A621DD-12MT L150X150X18 41077337 | A621DD-7MT L150X150X18 41077338 | A621DD-7MT L150X150X18 41077338 | A621DD-7MT L150X150X18 41077338 | A621DD-7MT L150X150X18 41077338 | A621DD-7MT L150X150X18 41077338 | A621DD-12MT L150X150X18 41077337 | A621DD-12MT L150X150X18 41077338 | A621DD-12MT L150X150X18 41077337 | A621DD-12MT L150X150X18 41077337 | A621DD-12MT L150X150X18 41077337 | A621DD-12MT L150X150X18 41077337 | A621DD-12MT L150X150X18 41077337 | A646DD-2MT LMIX 41077397/398 | A621DD-1MT L200X200X16 41077340 | A621DD-7MT L150X150X18 41077336 | A621DD-7MT L150X150X18 41077336 | A621DD-7MT L150X150X18 41077336 | A621DD-7MT L150X150X18 41077336 | A621DD-7MT L150X150X18 41077336 | A621DD-7MT L150X150X18 41077336 | A621DD-7MT L150X150X18 41077336 | A621DD-7MT L150X150X18 41077336 | A621DD-7MT L150X150X18 41077336 | N602-S-1.5MT L200X200X16 41077542 | A621DD-7MT L150X150X18 41077336 | N602-S-1.5MT L200X200X16 41077542 | N602-S-1.5MT L200X200X16 41077463 | A621DD-3.5MT L MIX 41077341/342 | N602-S-1.5MT L200X200X16 41077542 | A621DD-8MT L150X150X20 41077339 |  |  |  | H250X25(000080135239)(TC922) | H250X25(000080135239)(TC922) | H250X25(000080135239)(TC922) | H250X25(000080135412)(TC922)
| TOTAL WEIGHT | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 51 | 51 | 51 | 51 | 51 | 51 | 51 |  | S: 94; S: 94; HG: 94; B: 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 507 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 54 | 94 | 54 | 54 | 94 | 54 | 94 |  |  |  | 16628 | 16628 | 16628 | 13302.4
| NO. OF SET UPS | [40 empty] | 2 | [16 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
| NO OFOPERATION | [39 empty] | 3 | 600 | [12 empty] | not run | [6 empty] | 0 | 0 | 0 | 0
| SECONDARY LOAD | 3600 | 3600 | 7000 | 7000 | 12400 | 12400 | 20000 | 20000 | 20000 | 20000 | 22000 | 22000 | 22000 | 9000 | 2600 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | NOT RUN AS P | NOT RUN AS P | [5 empty] | 20000 | 20000 | 20000 | 20000 | 21500 | 21500 | 21500 | 740 | 740 | 881 | 881 |  |  |  |  | 1270 MIN | 1270 MIN | 1270 MIN | 1270 MIN | 1270 MIN | 1270 MIN | 1273 MIN | 1273 MIN | 1273 MIN | 1273 MIN | 801 MIN | 801 MIN | 801 MIN | 801 MIN
| CAL. RUN TIME | S+B | S+B | S+B | S+B | S+B | S+B | S+B | S+B | S+B | S | S | S | S | S | S | S | [11 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S+HG | HG | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S |  |  |  | 16.1442 | 16.1442 | 16.1442 | 13.7653 | bar: S to B
CP-09 | PROJECT SECTION (MIR) | [57 empty] | H150X10(000080134027)(TC928)H150X10(000080134053)(TC928) | H120X7(000080133812)(TC928) | H150X16(000080133273)(TB901)H200X16(000080133274)(TB901) |  |  |  | H120X8(000080135039)(TC922) | H120X8(000080135039)(TC922)
| TOTAL WEIGHT | [57 empty] | 2637.548 | 5439.4 | 1457.632 |  |  |  | 21402.1331 | 21402.1331
| NO. OF SET UPS | [57 empty] | 5 | 4 | 4 | 0 | 0 | 0 | 18 | 18 | 0
| NO OFOPERATION | [57 empty] | 770 | 1712 | 0 |  |  |  | 0 | 0
| SECONDARY LOAD | [57 empty] | N+ | N+N+B+ |  |  |  |  | B+N+N+B+ | B+N+N+B+
| CAL. RUN TIME | [57 empty] | 39.838 | 72.2317 | 95.46 |  |  |  | 267.6898 | 267.6898
CP-10 | PROJECT SECTION (MIR)
TOTAL WEIGHT
NO. OF SET UPS
NO OFOPERATION
SECONDARY LOAD
CAL. RUN TIME
CP-11 | PROJECT SECTION (MIR)
TOTAL WEIGHT
NO. OF SET UPS
NO OFOPERATION
SECONDARY LOAD
CAL. RUN TIME
CP-19 | PROJECT SECTION (MIR)
TOTAL WEIGHT
NO. OF SET UPS
NO OFOPERATION
SECONDARY LOAD
CAL. RUN TIME
CP-20 | PROJECT SECTION (MIR)
TOTAL WEIGHT
NO. OF SET UPS
NO OFOPERATION
SECONDARY LOAD
CAL. RUN TIME
CP-21 | PROJECT SECTION (MIR)
TOTAL WEIGHT
NO. OF SET UPS
NO OFOPERATION
SECONDARY LOAD
CAL. RUN TIME
PROJECT SECTION (MIR)
TOTAL WEIGHT
NO. OF SET UPS
NO OFOPERATION
SECONDARY LOAD
CAL. RUN TIME
plan compliances
LOAD/LOT.
PAB-44
plan compliances
LOAD/LOT.
WELDED
plan compliances
LOAD/LOT.
HEEL CUTTING (by mechanical mc)
plan compliances
LOAD/LOT.
BAND SAW
GRINDING/HG/ GAS NOTCHING
PLANNED OUTPUT
ACTUAL OUTPUT.
% PERFORMANCE WITH RESPECT TO OUTPUT
NO OF MACINE PLAN
NO OF MACHINE DID NOT RUN AS PER PLAN
% PLAN COMPLIENCE
NET HANDING OVER
SHIFT INCHARGE
Machine compliance report
| CP01 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| CP02 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| CP03 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| CP04 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| CP05 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| CP06 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| DB363 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| SUM | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 6 | 5 | 4 | 5 | 6 | 6 | 6 | 7 | 4 | 5 | 7 | 6 | 5 | 5 | 5 | 7 | 6 | 6 | 6 | 4 | 7 | 6 | 7 | 7 | 6 | 5 | 7 | 6 | 7 | 7 | 7 | 6 | 7 | 7 | 7 | 6 | 6 | 4 | 6 | 6 | 6 | 7 | 7 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| % | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 85.7143 | 71.4286 | 57.1429 | 71.4286 | 85.7143 | 85.7143 | 85.7143 | 100 | 57.1429 | 71.4286 | 100 | 85.7143 | 71.4286 | 71.4286 | 71.4286 | 100 | 85.7143 | 85.7143 | 85.7143 | 57.1429 | 100 | 85.7143 | 100 | 100 | 85.7143 | 71.4286 | 100 | 85.7143 | 100 | 100 | 100 | 85.7143 | 100 | 100 | 100 | 85.7143 | 85.7143 | 57.1429 | 85.7143 | 85.7143 | 85.7143 | 100 | 100 | 85.7143 | 85.7143 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
88.9163
JULY UP TO DATE